## Raw Tickets
NILE Pipeline Issues — April 2026
Key | Summary | Category | Status | Issue Type | Priority | Assignee | Reporter | Created | Resolution | Labels
NILE-1001 | Pipeline failed for client ABC data load | Data Issue | Done | Bug | High | Birajan | Ram | 2025-04-01
NILE-1002 | File not received from vendor XYZ | File Issue | In Progress | Bug | Critical | Birajan | Sita | 2025-04-01 |  | data-team
NILE-1003 | Schema change detected in raw table | Schema Issue | Open | Bug | Medium | Ram | Hari | 2025-04-02
NILE-1004 | Request for new pipeline for client DEF | Request | Done | Task | Low | Sita | Birajan | 2025-04-02 | Done | request
NILE-1005 | Unmatched raw count issue in member table | Data Issue | Open | Bug | High | Birajan | Ram | 2025-04-03
NILE-1006 | Spooler not running since last night | File Issue | Done | Bug | Critical | Ram | Sita | 2025-04-03
NILE-1007 | Pipeline schedule missed for morning run | Pipeline Schedule | Open | Bug | High | Birajan | Hari | 2025-04-04
NILE-1008 | Data mismatch found in claim output | Data Issue | In Progress | Bug | High | Sita | Birajan | 2025-04-04
NILE-1009 | Config error in pipeline after deployment | Pipeline Configuration | Done | Bug | Medium | Hari | Ram | 2025-04-05 | Done
NILE-1010 | Hadoop cluster unreachable from pipeline | Hadoop Issue | Open | Bug | Critical | Birajan | Sita | 2025-04-05 |  | hadoop
NILE-1011 | File missing for April 5th batch | File Issue | Done | Bug | High | Ram | Birajan | 2025-04-06 | Done
NILE-1012 | Request for access to reporting dashboard | Request | Done | Task | Low | Sita | Hari | 2025-04-07 | Done | request
NILE-1013 | Pipeline stuck after schema drift | Pipeline Issue | Open | Bug | High | Birajan | Ram | 2025-04-07
NILE-1014 | Raw count mismatch on eligibility file | File Issue | Open | Bug | Medium | Ram | Sita | 2025-04-08
NILE-1015 | Pipeline configuration update needed | Pipeline Configuration | Done | Task | Medium | Hari | Birajan | 2025-04-08 | Done
NILE-1016 | Empty file received from client GHI | File Issue | Open | Bug | High | Birajan | Ram | 2025-04-09
NILE-1017 | Hive query timeout on large dataset | Hadoop Issue | Done | Bug | High | Ram | Sita | 2025-04-09 | Done
NILE-1018 | ETL job failed for nightly processing | Pipeline Issue | Open | Bug | Critical | Sita | Birajan | 2025-04-10
NILE-1019 | Column removed from source without notice | Schema Issue | Open | Bug | High | Birajan | Hari | 2025-04-10
NILE-1020 | Request to update pipeline schedule | Pipeline Schedule | Done | Task | Low | Ram | Sita | 2025-04-11 | Done | request
NILE-1021 | Pipeline not started at expected time | Pipeline Schedule | Open | Bug | High | Hari | Birajan | 2025-04-11
NILE-1022 | Invalid data in member demographics file | File Issue | In Progress | Bug | High | Birajan | Ram | 2025-04-12
NILE-1023 | Spool error blocking file delivery | File Issue | Open | Bug | Critical | Ram | Sita | 2025-04-13
NILE-1024 | File not received for April 13th | File Issue | Done | Bug | High | Sita | Birajan | 2025-04-13 | Done
NILE-1025 | New pipeline requirement for client JKL | Data Issue | Open | Task | Low | Birajan | Hari | 2025-04-14 |  | request
NILE-1026 | ETL pipeline broken after config change | Pipeline Issue | Done | Bug | High | Ram | Birajan | 2025-04-14 | Done
NILE-1027 | Delayed pipeline run affecting SLA | Pipeline Schedule | Open | Bug | High | Sita | Ram | 2025-04-15
NILE-1028 | Unmatched records in provider table | Unmatched Raw Count | Open | Bug | Medium | Birajan | Sita | 2025-04-15
NILE-1029 | Namenode issue on hadoop cluster | Hadoop Issue | Done | Bug | Critical | Ram | Hari | 2025-04-16 | Done
NILE-1030 | Incorrect data type in schema definition | Data Issue | Open | Bug | High | Hari | Birajan | 2025-04-16
NILE-1031 | Pipeline schedule not aligned with SLA | Pipeline Schedule | Open | Task | Medium | Birajan | Ram | 2025-04-17
NILE-1032 | Source file rejected by validation | File Issue | Done | Bug | High | Ram | Sita | 2025-04-17 | Done
NILE-1033 | Data discrepancy in final claim output | Data Issue | Open | Bug | High | Sita | Birajan | 2025-04-18
NILE-1034 | Request to onboard new data source | Data Issue | Done | Task | Low | Birajan | Hari | 2025-04-18 | Done | request
NILE-1035 | Job failed due to transform error | Pipeline Issue | Open | Bug | Critical | Ram | Sita | 2025-04-19
NILE-1036 | Pipeline parameter misconfigured | Pipeline Configuration | Done | Bug | High | Hari | Birajan | 2025-04-19 | Done
NILE-1037 | Unknown processing error in batch run | Other / Uncategorized | Open | Bug | Medium | Birajan | Ram | 2025-04-20
NILE-1038 | File missing from SFTP landing zone | File Issue | Open | Bug | High | Ram | Sita | 2025-04-20
NILE-1039 | Spooler down after server restart | Spooler Issue | Done | Bug | Critical | Sita | Hari | 2025-04-21 | Done
NILE-1040 | Schema drift detected in claims feed | Schema Issue | Open | Bug | High | Birajan | Ram | 2025-04-21
NILE-1041 | Pipeline stuck in running state | Pipeline Issue | Open | Bug | Critical | Ram | Sita | 2025-04-22
NILE-1042 | Request for monthly report automation | Request | Done | Task | Low | Hari | Birajan | 2025-04-22 | Done | request
NILE-1043 | Wrong data loaded into member table | Data Issue | Open | Bug | High | Sita | Ram | 2025-04-23
NILE-1044 | Hadoop job timed out overnight | Hadoop Issue | Done | Bug | High | Birajan | Hari | 2025-04-23 | Done
NILE-1045 | Schedule delay for end of month run | Pipeline Schedule | Open | Bug | High | Ram | Birajan | 2025-04-24
NILE-1046 | Unmatched count in eligibility records | Data Issue | Open | Bug | Medium | Sita | Ram | 2025-04-24
NILE-1047 | Pipeline configuration change request | Data Issue | Done | Task | Low | Birajan | Hari | 2025-04-25 | Done | request

## Monthly Summary
NILE Pipeline Issue Summary — April 2026
Total Tickets: 47
Category | Count | % Share | Color Tag
File Issue | 10 | 21.3%
Data Issue | 10 | 21.3%
Pipeline Issue | 5 | 10.6%
Spooler Issue | 1 | 2.1%
Pipeline Configuration | 3 | 6.4%
Unmatched Raw Count | 1 | 2.1%
Pipeline Schedule | 6 | 12.8%
Schema Issue | 3 | 6.4%
Hadoop Issue | 4 | 8.5%
Request | 3 | 6.4%
Other / Uncategorized | 1 | 2.1%

## Needs Review
Uncategorized Tickets — needs manual category (1 tickets)
Key | Summary | Status | Created | Labels
NILE-1037 | Unknown processing error in batch run | Open | 2025-04-20